## Sheet1
PROJECT NUMBER | 2,(Team 44)
PROJECT NAME | Speech2SpeechBuffer
PROJECT MENTOR (sponsor) | Harpreet (TA), Satish(Client) | [7 empty] | Done
Ongoing
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error % | Planned
Week 1 (January 15- January 21)
Fix meeting with client | Coordination | Karthik | 0.5 | 0.5 |  |  | 0 | 0
GIT Repository setup | Coordination | Arya | 0.5 | 0.5 |  |  | 0 | 0
Client meeting | Coordination | Everyone | 1 | 1 |  |  | 0 | 0
RabbitMQ | Learn | Everyone | 3 | 2 |  |  | 1 | 33.3333
FAST API | Learn | Everyone | 3 | 1 |  |  | 2 | 66.6667
Json Structures | Learn | Everyone | 0.5 | 0.5 |  |  | 0 | 0
Project synopsis discuss | Coordination | Varun,Akash | 2 | 0.5 |  |  | 1.5 | 75
Project Plan discuss | Coordination | Varun,Akash | 3 | 0.5 |  |  | 2.5 | 83.3333
MoM | Coordination | Karthik | 2 | 2 |  |  | 0 | 0
Team Meeting | Coordination | Arya | 2 | 2 |  |  | 0 | 0
Status tracker | Coordination | Arya,Prashant | 1 | 1 |  |  | 0 | 0
Week 2 (January 22 - January 28)
Fix meeting with client | Coordination | Karthik | 0.5 | 0.5
Client meeting | Coordination | Prashanth | 0.5 | 0.5
RabbitMQ | Learn | Everyone | 1 | 1
FAST API | Learn | Everyone | 3 | 1
Json Structures | Learn | Everyone | 0.5 | 0.5
Project synopsis writeup | Coordination | Varun,Akash | 2 | 1.5
Project Plan writeup | Coordination | Varun,Akash | 3 | 2.5
MoM | Coordination | Karthik | 2 | 2
Team Meeting | Coordination | Arya | 2 | 3
Status tracker | Coordination | Arya,Prashant | 0.5 | 0.5
Week 3 (January 29 – Feb 4)
Fix meeting with client | Coordination | Karthik | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
RabbitMQ server setup( localhost) | Coordination | Varun,Arya | 0.5 | 1
python environment setup | Coordination | Varun,Arya | 0.5 | 0.5
Running Document | Coordination | Akash | 1.5 | 2
Code (Servers) – Prototype | Coordination | Arya,Varun | 2 | 2.5
MoM | Coordination | Arya,Prashanth | 2 | 2
Team Meeting | Coordination | Prashanth | 2 | 3
Status tracker | Coordination | Varun,Akash | 0.5 | 0.5
Week-4 (Feb 5- Feb-11)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
RabbitMQ server setup(cloud) | Coordination | Arya | 0.5 | 1
environment setup (Final) | Coordination | Varun | 0.5 | 0.5
Test Plan doc | Coordination | Prashanth | 1.5 | 2
Document ( errors handling for client) | Coordination | Varun,Akash | 2 | 2.5
Code (Servers) – Final code | Coordination | Arya,Varun | 5 | 6
Testing (Edge cases, Errors logging) | Coordination | Varun,Arya,Akash | 3 | 4
MoM | Coordination | Karthik | 2 | 2
Team Meeting | Coordination | Prashanth | 2 | 3
Status tracker | Coordination | Varun | 0.5 | 0.5
Week-5 (Feb 12- Feb 18)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
SRS | Coordination | Akash,Karthik,Varun,Arya | 4 | 5
Requirements for Phase-1 (Final) | Coordination | Akash, Karthik | 1.5 | 2
Design Doc for Phase-1 (Final) | Coordination | Arya, Varun | 1.5 | 2
Test Doc for client (Final) | Coordination | Varun,Akash | 2 | 2.5
Code (Servers) – Final code | Coordination | Akash,Varun,Arya | 4 | 5
Testing (Network Errors, Timeouts) | Coordination | Varun,Arya,Prashanth | 3 | 4
Project-Plan update | Coordination | Varun,Akash | 0.5 | 0.5
MoM | Coordination | Karthik | 2 | 2
Team Meeting | Coordination | Prashanth | 2 | 3
Status tracker | Coordination | Varun | 0.5 | 0.5
Week-6 (Feb 19 – Feb 25)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Phase-2 Requirements Document | Coordination | Varun,Akash | 2 | 2.5
Design Doc for Phase-2 | Coordination | Arya, Karthik | 1.5 | 2
API calls inside FastAPI | Learn | Everyone | 2 | 3
Dummy SandBox interaction | Learn | Everyone | 2 | 2.5
Code Execution Guidelines Doc | Coordination | Varun,Prashanth | 0.5 | 1
Design Doc for Phase-1(update) | Coordination | Arya,Akash | 0.5 | 0.5
Exploring queue deletion Methods | Learn | Karthik,Prashanth | 1 | 2
MoM | Coordination | Karthik | 2 | 2
Team Meeting | Coordination | Prashanth | 2 | 3
Status tracker | Coordination | Varun | 0.5 | 0.5
Week-7 (Feb 26 – Mar 4)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Updated SRS | Coordination | Akash,Karthik | 1 | 1.5
Updated Guidelines Doc | Coordination | Varun,Arya | 0.5 | 0.5
API calls inside FastAPI | Learn | Everyone | 2 | 0.5
Dummy SandBox interaction | Learn | Everyone | 2 | 45 Min
Design Doc for Phase-1(update) | Coordination | Arya,Akash | 0.5 | 0.5
Exploring queue deletion Methods | Learn | Karthik,Prashanth | 1 | 0.5
MoM | Coordination | Karthik | Meeting Cancelled | 5 Min
Team Meeting | Coordination | Prashanth | 2 | 1.5
Status tracker | Coordination | Varun | 0.5 | 0.5
Week-8 (Mar 4 – Mar 11)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Design Document | Coordination | Team | 3 | 3
Integrate ASR API | Coordination | Varun,Akash | 2 | 2
Integrate MT API | Coordination | Arya,Karthik | 2 | 2
Integrate TTS API | Coordination | Karthik,Akash | 2 | 2
Fetch & Authenticate from Anuvaad | Coordination | Arya,Varun | 1.5 | 2
Test flow b/w ARS-MT-TTS | Coordination | Prashanth | 1 | 1.5
MoM | Coordination | Karthik | 1 1 | 1
Team Meeting | Coordination | Prashanth | 2 | 1.5
Status tracker | Coordination | Varun,Akash | 0.5 | 0.5
Week-9 (Mar 11 – Mar 18)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Integrate locally tested ASR API | Coordination | Varun,Akash | 2 | 2
Integrate locally tested MT API | Coordination | Arya,Karthik | 2 | 2
Integrate locally TTS API | Coordination | Karthik,Akash | 2 | 2
Handle Audio with diff wpm | Coordination | Arya,Varun | 1.5 | 2
Errors,edge cases in RabbitMQ Flow | Coordination | Arya,Varun | 2 | 2
Modify generateaudio code | Coordination | Prashanth | 1 | 1.5
MoM | Coordination | Akash | 0.5 1 | 0.5
Team Meeting | Coordination | Prashanth | 2 | 1.5
Status tracker | Coordination | Akash | 0.5 | 0.5
Week-10 (Mar 18 – Mar 25)
Fix meeting with client | Coordination | Akash,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Implement chunking | Coordination | Varun,Akash | 2 | 3
Add timeout mechanism | Coordination | Arya,Karthik | 2 | 2.5
Implement rate-limiting to restrict APIs | Coordination | Karthik,Akash | 2 | 2
Handle Audio with diff wpm | Coordination | Arya,Varun | 0.5 | 0.5
Run servers on diff systems,environments | Coordination | Prashanth | 1 | 2
MoM | Coordination | Karthik | 0.5 1 | 0.5
Team Meeting | Coordination | Prashanth | 2 | 1.5
Status tracker | Coordination | Akash | 0.5 | 0.5
Week-11 (Mar 25 – Apr 1)
Fix meeting with client | Coordination | Akash,Varun,Arya | 0.5 | 0.5
Client meeting | Coordination | Karthik | 0.5 | 0.5
Integrate Streaming API’s | Coordination | Varun,Akash | 2 | 3
Change and Optimize ASR processing | Coordination | Arya,Karthik | 2 | 2.5
Support Parallel Requests | Coordination | Karthik,Akash | 1.5 | 2
Conduct Multi-system testing | Coordination | Prashanth | 1 | 2
MoM | Coordination | Arya | 0.5 1 | 0.5
Team Meeting | Coordination | Prashanth | 2 | 1.5
Status tracker | Coordination | Varun | 0.5 | 0.5